## Risks
Risk Register
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional) ¦ All figures simulated
ID | Risk Description | Category | Likelihood | Impact | Severity | Owner | Mitigation | Status
R001 | Content migration proves more complex than estimated due to inconsistent legacy metadata | Delivery | High | High | High | Migration Lead | Phase migration by region; reassess estimate after Wave 1 | Occurred — see Decision 001
R002 | AI/RAG assistant surfaces client-confidential content across an ethical wall | Compliance | Medium | High | High | Technology Lead | Confidentiality-aware access design scoped as a hard requirement prior to AI rollout | Open
R003 | Low adoption due to billable-hour incentive structure discouraging knowledge contribution | Adoption | High | Medium | High | Change Lead | Incentive and recognition redesign; staffing credit for debrief completion | Open
R004 | Cross-border data residency requirements delay platform hosting decisions in specific regions | Regulatory | Medium | Medium | Medium | Program Manager | Engage regional compliance early; regional hosting options assessed per jurisdiction | Open
R005 | Key regional knowledge governance contacts turn over during the program | Resourcing | Medium | Medium | Medium | Regional Leads | Document governance responsibilities; identify backup contacts per region | Open
R006 | Vendor delay in platform implementation services | Vendor | Low | High | Medium | Technology Lead | Contractual milestones with penalty clauses; contingency reserve allocated | Open
R007 | Search and AI evaluation metrics fall short of target during pilot | Delivery | Medium | Medium | Medium | Technology Lead | Iterative sprint-based improvement; extend pilot period if needed | Open

## Assumptions
Assumptions Log
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional) ¦ All figures simulated
ID | Assumption | Area | Validation Approach | Owner | Status
A001 | Regional offices will provide a designated Knowledge Governance contact | Governance | Confirm nomination during Discovery phase | Program Manager | Confirmed
A002 | Existing identity and access management system can be extended to support ethical-wall access model | Technology | Technical spike during Sprint 0 | Technology Lead | Confirmed
A003 | Executive sponsorship and budget remain stable for the 18-month duration | Governance | Reconfirmed at each Steering Committee gate | Executive Sponsor | Ongoing
A004 | Legacy content sources remain accessible for audit and migration throughout the program | Delivery | Verified during knowledge audit | Migration Lead | Confirmed

## Issues
Issue Log
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional) ¦ All figures simulated
ID | Issue Description | Raised By | Date Raised | Priority | Owner | Resolution | Status
I001 | Migration complexity 30% above original estimate after Wave 1 audit | Migration Lead | Month 5 | High | Program Manager | Budget reallocated from contingency; see Decision 001 | Resolved
I002 | Two regional offices flagged conflicting taxonomy preferences | Regional Leads (EMEA, APAC) | Month 3 | Medium | Knowledge Governance Lead | Federated model adopted; see Decision 002 | Resolved

## Dependencies
Dependency Log
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional) ¦ All figures simulated
ID | Dependency Description | Depends On | Impact if Delayed | Owner | Status
D001 | Migration wave planning depends on completion of knowledge audit | Knowledge Audit | Delays start of Wave 1 migration | Migration Lead | On Track
D002 | AI/RAG rollout depends on confidentiality-aware access design sign-off | Access Design Approval | Delays AI pilot launch | Technology Lead | On Track
D003 | Regional go-live depends on regional governance contact onboarding | Governance Onboarding | Delays regional rollout wave | Regional Leads | On Track