## Schedule and WBS
Schedule and Work Breakdown Structure
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional) ¦ Start date: 1-Jan-2026 (simulated)
WBS ID | Task / Milestone | Phase | Start (Month) | End (Month) | Duration (Months) | Owner | Status
1.0 | Discovery & Design | Discovery | 1 | 3 | 2 | Program Manager | Complete
1.1 | Knowledge audit (by office/region) | Discovery | 1 | 2 | 1 | Migration Lead | Complete
1.2 | Taxonomy and information architecture design | Discovery | 2 | 3 | 1 | Knowledge Governance Lead | Complete
1.3 | Governance model and ethical-wall requirements defined | Discovery | 2 | 3 | 1 | Knowledge Governance Lead | Complete
2.0 | Build & Migration | Build | 4 | 13 | 9 | Technology Lead | In Progress
2.1 | Platform configuration | Build | 4 | 6 | 2 | Technology Lead | Complete
2.2 | Migration Wave 1 — EMEA | Build | 5 | 8 | 3 | Migration Lead | Complete
2.3 | Migration Wave 2 — Americas | Build | 8 | 11 | 3 | Migration Lead | In Progress
2.4 | Migration Wave 3 — APAC | Build | 11 | 13 | 2 | Migration Lead | Not Started
2.5 | AI/RAG assistant — Sprints 0-6 (see Agile backlog) | Build | 6 | 13 | 7 | Technology Lead | In Progress
3.0 | Pilot & Iteration | Pilot | 10 | 14 | 4 | Technology Lead | Not Started
3.1 | AI Search Pilot (50 users) | Pilot | 10 | 12 | 2 | Technology Lead | Not Started
3.2 | Employee Beta (expanded pilot) | Pilot | 12 | 14 | 2 | Change Lead | Not Started
4.0 | Global Rollout | Rollout | 14 | 17 | 3 | Program Manager | Not Started
4.1 | Regional go-live — EMEA | Rollout | 14 | 15 | 1 | Regional Lead (EMEA) | Not Started
4.2 | Regional go-live — Americas | Rollout | 15 | 16 | 1 | Regional Lead (Americas) | Not Started
4.3 | Regional go-live — APAC | Rollout | 16 | 17 | 1 | Regional Lead (APAC) | Not Started
5.0 | Stabilization & Closure | Closure | 17 | 18 | 1 | Program Manager | Not Started
5.1 | Benefits realization review | Closure | 17 | 18 | 1 | Program Manager | Not Started
5.2 | Project closure and retrospective | Closure | 18 | 18 | 0 | Program Manager | Not Started