## Stakeholder Register
Stakeholder Register
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional)
ID | Stakeholder / Group | Type | Practice / Region | Interest | Influence | Preferred Communication | Engagement Strategy
S001 | Executive Sponsor (Global Managing Partner) | Executive | Global | High | High | Steering committee deck, escalation email | Monthly steering updates; involve in all major decisions
S002 | Program Steering Committee | Executive | Global | High | High | Steering committee deck | Gate reviews; decision approvals
S003 | Regional Managing Partners | Executive | Regional (NA, EMEA, APAC) | Medium | High | Executive status report | Regional briefings ahead of each migration wave
S004 | Knowledge Governance Lead | Project Team | Global | High | Medium | Weekly working session | Direct collaboration on taxonomy and governance design
S005 | Regional Knowledge Contacts | Project Team | Regional (per office) | High | Medium | Weekly update, working sessions | Involve in content audit and classification review
S006 | Practice Area Leaders | Project Team | By Practice | Medium | Medium | Sprint announcement, briefing email | Consulted during taxonomy design for practice-specific needs
S007 | Consultants (end users) | Employees | Global | Medium | Low | Newsletter, FAQ, in-platform guidance | Training, adoption campaigns, feedback channels
S008 | IT / Platform Engineering | Project Team | Global | High | Medium | Technical working session | Embedded in technology workstream
S009 | Compliance & Data Privacy Office | Governance | Global | High | High | Governance review meeting | Early and ongoing engagement on ethical walls and data residency
S010 | HR / People Team | Governance | Global | Medium | Medium | Briefing email | Consulted on incentive design and offboarding knowledge capture