## Go Live Checklist
Go-Live Checklist — EMEA Wave
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional)
Category | Checklist Item | Owner | Status | Notes
Content Readiness | Wave 1 (EMEA) migration classification audit passed | Knowledge Governance Lead | Done | 90%+ threshold met
Content Readiness | Duplicate and stale content flagged and resolved | Migration Lead | Done
Platform Readiness | Performance testing completed for expected EMEA user load | Technology Lead | Done
Platform Readiness | Search functionality verified against Sprint 3 acceptance criteria | Technology Lead | Done
Confidentiality Readiness | Ethical-wall access control testing signed off | Compliance & Data Privacy Office | Done | Zero critical findings
Confidentiality Readiness | Cross-border data residency requirements verified for EMEA hosting | Compliance & Data Privacy Office | Done
Change Readiness | Training sessions delivered to EMEA consultants | Change Lead | Done
Change Readiness | Go-live announcement communication drafted and approved | Change Lead | Pending | Scheduled for send on go-live day
Change Readiness | Support channel and FAQ published | Change Lead | Pending | Final review in progress
Governance Readiness | Regional Knowledge Governance contact active and onboarded | Regional Lead (EMEA) | Done
AI Assistant (Trailing Feature) | AI assistant held back pending threshold achievement | Technology Lead | Pending | Per Decision 003 — not required for go-live
% Complete | 72.73%