## Migration Wave Plan
Migration Wave Plan
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional) ¦ All figures simulated
Wave | Region | Start Month | End Month | Est. Documents | Migrated (Actual) | % Complete | Status | Notes
Wave 1 | EMEA | 5 | 8 | 4800 | 4800 | 100% | Complete | Legacy metadata quality lower than estimated — triggered Decision 001
Wave 2 | Americas | 8 | 11 | 5600 | 3920 | 70% | In Progress | Automated cleanup utility deployed ahead of this wave per Decision 001
Wave 3 | APAC | 11 | 13 | 3900 | 0 | 0% | Not Started | Scheduled to begin after Wave 2 completion
Total |  |  |  | 14300 | 8720 | 60.98%