## Budget vs Actual
Budget vs. Actual — As of Month 13
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional) ¦ All figures simulated
Category | Baseline Budget (EUR) | Actual Spend To Date (EUR) | Variance (EUR) | Variance % | Notes
Platform Licenses | 180000 | 175000 | -5000 | -2.778% | Slightly under; final license tier confirmed lower than estimated
Implementation | 200000 | 188000 | -12000 | -6% | On track; Wave 3 implementation work remaining
Migration | 120000 | 132000 | 12000 | 10% | Over baseline — see Decision 001 (contingency draw applied)
Integration | 80000 | 74000 | -6000 | -7.5% | On track
AI / Search | 70000 | 61000 | -9000 | -12.86% | On track; Sprint 5-6 retuning work within budget
Training | 40000 | 22000 | -18000 | -45% | Under; regional training for Americas and APAC not yet delivered
Change Management | 30000 | 19000 | -11000 | -36.67% | Under; adoption campaigns ramp up closer to go-live
Contingency | 30000 | 15000 | -15000 | -50% | €15,000 drawn per Decision 001; €15,000 remaining reserve
Total | 750000 | 686000 | -64000 | -8.533%