## Change Request Log
Change Request Log
Project Lighthouse — Knowledge Infrastructure Workstream ¦ Solstice Advisory (fictional)
CR ID | Description | Requested By | Date | Impact (Budget / Schedule / Scope) | Routing | Approver | Status | Related Decision
CR001 | Increase migration budget / add automation tooling due to Wave 1 complexity | Migration Lead | Month 5 | Budget: +€15,000 (contingency) | Steering Committee (≥€10,000 threshold) | Program Steering Committee | Approved | Decision 001
CR002 | Adopt federated taxonomy model to resolve EMEA/APAC classification conflict | Knowledge Governance Lead | Month 3 | Scope: information architecture approach | Steering Committee (scope change) | Program Steering Committee | Approved | Decision 002
CR003 | Decouple AI assistant release from EMEA go-live date | Technology Lead | Month 13 | Schedule: AI feature delayed ~3-4 weeks | Steering Committee (schedule change) | Program Steering Committee | Approved | Decision 003
CR004 | Add expert-finder integration to AI assistant backlog | Practice Area Leaders | Month 13 | Budget: <€10,000 (absorbed in existing AI/Search line) | Auto-approved (Project Manager) | Project Manager | Approved | —