## Benefits Realization
Benefits Realization — Program Close
Project Lighthouse — Knowledge Infrastructure Program ¦ Solstice Advisory (fictional) ¦ All figures simulated
KPI | Baseline | Target | Actual (at Close) | Status | Notes
Documents with owner | 42% | 95% | 94% | Partially Met | Just under target; remaining gap in APAC long-tail content
Documents with metadata | 35% | 90% | 91% | Met
Content reviewed | 28% | 90% | 88% | Partially Met | Slight shortfall; ongoing via Stale Content Alerts automation
Duplicate content | 31% | <10% | 9% | Met
Search success rate | 54% | 85% | 86% | Met | Achieved after Sprint 5-6 retuning
AI-answer grounding accuracy | — | 95% | 96% | Met | Achieved prior to full AI assistant release
Active usage (3 months post-launch) | — | 70% | 74% | Met | EMEA and Americas combined; APAC still ramping
Financial Benefit Summary
Item | Amount (EUR) | Notes
Total Program Investment | -750000 | Full approved budget
Estimated Annual Productivity Benefit | 1200000 | Based on 20% search efficiency improvement across consultant base
Net Year-1 Value (Benefit less Investment) | 450000
All figures are simulated/estimated for portfolio purposes. Actual productivity benefit realization would be measured over the 12 months following full rollout.