## Benefits Register
Transformation Benefits Register
Project Lighthouse ¦ Solstice Advisory (fictional) ¦ All figures simulated
Benefit | Type | Baseline | Target | Measurement Method | Owner | Realization Timeline
Recovered productivity from faster search | Financial (Quantified) | €0 | €1.2M / year | Estimated from search time reduction × consultant population × loaded hourly cost | Program Manager | Year 1 post full rollout
Faster proposal turnaround | Financial (Estimated) | Current avg. turnaround | 20% reduction | Time-to-submit tracked via proposal tool integration | Business Development Lead | Year 1
Reduced knowledge loss from attrition | Qualitative / Risk Reduction | No structured capture at offboarding | Offboarding debrief completed for 90%+ of departing consultants | Offboarding checklist completion rate | Ongoing from Month 14
Improved proposal win rate via better credential reuse | Financial (Indicative) | Current win rate | Directional improvement (not formally targeted) | Win/loss tracking, qualitative attribution | Business Development Lead | Year 1-2
Reduced compliance risk from ungoverned confidential content | Risk Reduction | Inconsistent access control across legacy sources | Zero confirmed ethical-wall breaches | Compliance incident tracking | Compliance & Data Privacy Office | Ongoing from launch
This register tracks program-level benefits over time. Delivery-level KPI outcomes at project closure are recorded in Lighthouse-PM-Delivery/Closure/Benefits Realization.xlsx.